## S1
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | % Progress | Task Owner
1 | Subscription Management | 1.01 | Secure User Authentication | Develop User Login System | 2024-03-02 | 2024-03-03 | 100% | Niyati
2 | Subscription Management | 1.01 | Secure User Authentication | Implement User Registration Functionality | 2024-03-05 | 2024-03-08 | 100% | Yakshita
3 | Subscription Management | 1.01 | Secure User Authentication | Implement Password Management Features | 2024-03-02 | 2024-03-03 | 100% | Niyati
4 | Subscription Management | 1.01 | Secure User Authentication | Testing Secure User Authentication funtionality | 2024-03-02 | 2024-03-03 | 100% | Niyati
5 | Subscription Management | 1.02 | Plan and Price Management | Design and Implement Subscription Plans | 2024-03-08 | 2024-03-09 | 100% | Shiva
6 | Subscription Management | 1.02 | Plan and Price Management | Develop Billing System | 2024-03-08 | 2024-03-09 | 100% | Shiva
7 | Subscription Management | 1.02 | Plan and Price Management | Testing Plan and Price Management funtionality | 2024-03-08 | 2024-03-09 | 100% | Shiva
8 | Subscription Management | 1.03 | Access Dedicated Customer Support | Implement Subscription Renewal System | 2024-03-07 | 2024-03-08 | 100% | Huzefa
9 | Subscription Management | 1.03 | Access Dedicated Customer Support | Integrate Customer Support Features | 2024-03-03 | 2024-03-04 | 100% | Pankti
10 | Subscription Management | 1.03 | Access Dedicated Customer Support | Testing Access Dedicated Customer Support funtionality | 2024-03-03 | 2024-03-04 | 100% | Pankti
11 | Subscription Management | 1.04 | View and Apply Discounts | Implement Discount Management Systems | 2024-03-05 | 2024-03-08 | 100% | Yakshita
12 | Subscription Management | 1.04 | View and Apply Discounts | Develop Ticketing System | 2024-03-05 | 2024-03-08 | 100% | Yakshita
13 | Subscription Management | 1.04 | View and Apply Discounts | Define Discount Eligibilty Criteria | 2024-03-05 | 2024-03-08 | 100% | Yakshita
14 | Subscription Management | 1.04 | View and Apply Discounts | Testing View and Apply Discounts funtionality | 2024-03-05 | 2024-03-08 | 100% | Yakshita

## S2
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | % Progress | Task Owner
1 | Sales Management | 2.01 | Analyze Data with Analytics and Reporting | Implement simple dashboard gui for analytics display | 03/19/24 | 03/22/24 | 100% | Shiva
2 | Sales Management | 2.01 | Analyze Data with Analytics and Reporting | Implement core functionality to get the data. | 2024-03-19 | 03/21/24 | 100% | Yakshita
3 | Sales Management | 2.01 | Analyze Data with Analytics and Reporting | Implement functionality where this feature can only be acccessed by premium users. | 2024-03-19 | 03/22/24 | 100% | Yakshita
4 | Sales Management | 2.01 | Analyze Data with Analytics and Reporting | Develop test cases for Analytics and Reporting functionality. | 2024-03-19 | 04/01/24 | 100% | Yakshita
5 | Sales Management | 2.01 | Analyze Data with Analytics and Reporting | Test Analytics and Reporting functionality. | 2024-03-19 | 04/01/24 | 100% | Yakshita
6 | Sales Management | 2.02 | Receive Deals Alerts & Notifications | Display a selectable discount alrerts (on/off) button on user dashboard | 2024-03-19 | 04/03/24 | 100% | Jayesh
7 | Sales Management | 2.02 | Receive Deals Alerts & Notifications | Implement core functionality to send discount alerts (emails) to user if its on. | 03/19/24 | 04/01/24 | 100% | Jayesh
8 | Sales Management | 2.02 | Receive Deals Alerts & Notifications | Implement a 'Wishlist' button for premium users. | 03/19/24 | 04/02/24 | 100% | Jayesh
9 | Sales Management | 2.02 | Receive Deals Alerts & Notifications | Implement core functionality to send email to the user as soon as any product from his wishlist is listen on market. | 03/19/24 | 03/22/24 | 100% | Jayesh
10 | Sales Management | 2.02 | Receive Deals Alerts & Notifications | Develop test cases for Receive Deals Alerts and Notification functionality. | 03/19/24 | 03/20/24 | 100% | Huzefa
11 | Sales Management | 2.02 | Receive Deals Alerts & Notifications | Test Receive Deals Alerts and Notification fucntionality. | 03/19/24 | 04/03/24 | 100% | Huzefa
12 | Sales Management | 2.03 | Integrate and Implement Marketing Strategies | Implement functionality for premiums user to display their product at top for 24H | 03/19/24 | 04/02/24 | 100% | Niyati
13 | Sales Management | 2.03 | Integrate and Implement Marketing Strategies | Create a button for premium user to display their product at top. | 03/19/24 | 04/02/24 | 100% | Huzefa
14 | Sales Management | 2.03 | Integrate and Implement Marketing Strategies | Develop test cases for Integrate and Implement Marketing Strategies functionality. | 03/19/24 | 04/01/24 | 100% | Shiva
15 | Sales Management | 2.03 | Integrate and Implement Marketing Strategies | Test Integrate and Implement Marketing Strategies fucntionality. | 03/19/24 | 04/03/24 | 100% | Shiva
16 | Financal Transaction Management | 3.01 | View Transaction History | Create a 'View History' button/option in user dashboard. | 03/19/24 | 04/04/24 | 100% | Yakshita
17 | Financal Transaction Management | 3.01 | View Transaction History | Create a page to display users transaction history | 03/19/24 | 2024-04-04 | 100% | Yakshita
18 | Financal Transaction Management | 3.01 | View Transaction History | Implement core functionality to get the data. | 03/19/24 | 2024-04-05 | 100% | Yakshita
19 | Financal Transaction Management | 3.01 | View Transaction History | Develop test cases for View Transaction History functionality. | 03/19/24 | 2024-04-06 | 100% | Niyati
20 | Financal Transaction Management | 3.01 | View Transaction History | Test View Transaction History functionality. | 03/19/24 | 2024-04-06 | 100% | Niyati

## S3
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | % Progress | Task Owner
1 | Financal Transaction Management | 3.02 | Manage Payment Methods | Implement Payment Method Form as create a form for users to input payment details | 2024-04-19 | 2024-04-21 | 100% | Niyati
2 | Financal Transaction Management | 3.02 | Manage Payment Methods | Integrate Payment Gateway API and connect the payment system to a third-party service for processing transactions | 2024-04-19 | 2024-04-21 | 100% | Yakshita
3 | Financal Transaction Management | 3.02 | Manage Payment Methods | Implement Premium Access Restrictio as restrict access to premium features based on subscription status | 2024-04-19 | 2024-04-22 | 100% | Niyati
4 | Financal Transaction Management | 3.02 | Manage Payment Methods | Display Payment Method Summary and show users a summary of their chosen payment methods | 2024-04-19 | 2024-04-23 | 100% | Jayesh
5 | Financal Transaction Management | 3.02 | Manage Payment Methods | Test the functionality to add, update, and delete payment methods to ensure seamless management of payment options | 2024-04-19 | 2024-04-23 | 100% | Niyati
6 | Financal Transaction Management | 3.02 | Manage Payment Methods | Implement Payment Method Verification as verify payment methods for security and authenticity | 2024-04-19 | 2024-04-23 | 100% | Niyati
7 | Financal Transaction Management | 3.03 | Process Returns and Refunds | Implement Return Request Form as develop a form for users to request returns on purchases | 2024-04-19 | 2024-04-24 | 100% | Shiva
8 | Financal Transaction Management | 3.03 | Process Returns and Refunds | Implement Partial Refunds: Enable refunds for partial amounts of transactions | 2024-04-19 | 2024-04-25 | 100% | Shiva
9 | Financal Transaction Management | 3.03 | Process Returns and Refunds | Test the process of initiating returns and refunds to verify accurate handling of transactions and timely reimbursement to users | 2024-04-19 | 2024-04-25 | 100% | Niyati
10 | Financal Transaction Management | 3.03 | Process Returns and Refunds | Automate Refund Approval Workflow as set up an automated process for approving refund requests | 2024-04-19 | 2024-04-25 | 100% | Shiva
11 | Financal Transaction Management | 3.03 | Process Returns and Refunds | Generate Refund Reports and create reports detailing refund transactions for analysis | 2024-04-19 | 2024-04-25 | 100% | Huzefa
12 | Financal Transaction Management | 3.03 | Process Returns and Refunds | Test the functionality for tracking and resolving disputes related to payments to ensure efficient resolution and customer satisfaction | 2024-04-19 | 2024-04-25 | 100% | Bansari
13 | Financal Transaction Management | 3.04 | Ensure Security & Fraud Prevention Measures | Implement Two-Factor Authentication (2FA) as add an extra layer of security requiring users to verify their identity through a secondary method | 2024-04-19 | 2024-04-26 | 100% | Pankti
14 | Financal Transaction Management | 3.04 | Ensure Security & Fraud Prevention Measures | Set Up Account Lockout Policy and establish rules to automatically lock out accounts after a certain number of failed login attempts | 2024-04-19 | 2024-04-26 | 100% | Yakshita
15 | Financal Transaction Management | 3.04 | Ensure Security & Fraud Prevention Measures | Test the implementation of security protocols and fraud prevention measures to verify robust protection of sensitive payment data and detection of fraudulent activities | 2024-04-19 | 2024-04-26 | 100% | Yakshita
16 | Financal Transaction Management | 3.04 | Ensure Security & Fraud Prevention Measures | Enable Transaction Monitoring as monitor transactions for suspicious activity or fraud | 2024-04-19 | 2024-04-26 | 100% | Yakshita
17 | Financal Transaction Management | 3.04 | Ensure Security & Fraud Prevention Measures | Create Security Audits as conduct regular audits to assess and improve the platform's security measures | 2024-04-19 | 2024-04-27 | 100% | Yakshita
18 | Advertising Management | 4.01 | Post more ads by Premium users | Create Premium Ad Packages as offer specialized advertising packages with enhanced features | 2024-04-19 | 2024-04-27 | 100% | Yakshita
19 | Advertising Management | 4.01 | Post more ads by Premium users | Implement Premium User Tier and introduce a tiered system where users can access premium features with a subscription | 2024-04-19 | 2024-04-28 | 100% | Yakshita
20 | Advertising Management | 4.01 | Post more ads by Premium users | Test and verify premium users who can successfully post ads without any glitches or errors. | 2024-04-19 | 2024-04-28 | 100% | Yakshita
21 | Advertising Management | 4.01 | Post more ads by Premium users | Modify Ad Posting Limit and adjust the number of advertisements users can post based on their subscription level | 2024-04-19 | 2024-04-28 | 100% | Jayesh
22 | Advertising Management | 4.01 | Post more ads by Premium users | Enable Ad Renewal for Premium Users as allow premium users to automatically renew their advertisements. | 2024-04-19 | 2024-04-29 | 100% | Huzefa
23 | Advertising Management | 4.01 | Post more ads by Premium users | Implement Ad Approval Priority for Premium Users as prioritize the approval of advertisements submitted by premium users. | 2024-04-19 | 2024-04-29 | 100% | Jayesh